## Sheet1
| Monday 30/5 | Tuesday 31/5 | Wednesday 1/6 | Thursday 2/6 | Friday 3/6 | Monday 6/6 | Tuesday 7/6 | Wednesday 8/6 | Thursday 9/6 | Friday 10/6
Overall |  | Consultancy Stuff |  |  |  | OFF | Consultancy Stuff | DEMO DAY | Consultancy Stuff
Questions for Robert
Deji |  | Personal | [5 empty] | Demo Prep | Personal
|  |  |  | Adding Pallets (Logic Fix) |  |  | Administration Initial Check CRUD
Manon |  | Personal | [5 empty] | Demo Prep | Personal
[7 empty] | Notes Implemented |  |  | Business Logic (Current) |  | Modals
Nick |  | Personal |  | Changing Pallet Location Button |  |  |  | Demo Prep | Personal | New Business Logic |  | Finish Production Styling + hourly reports styling
|  | Site Visit |  |  | Add Stand-up Notes Online |  | Update Hourly Check-up |  | Research Modals |  |  | Change navigation to "sections"
Noah |  | Personal |  |  | Drawings Style Update + Add to Admin |  |  | Demo Prep | Personal |  |  | Timestamp Calculations
|  | Site Visit |  |  |  |  | Truck Driver
Shirel |  | Personal | Fix navigation |  |  |  |  | Demo Prep | Personal |  |  | Business Process
|  |  | Picking Production Line |  | Update Order Status |  | Creating new order (2-step form) |  | Implement "Section" |  |  | Pick our features
| Team Roles |  |  | Goal:
| Team Coach | Nick |  | 1 | Finish Production/Admin view styling and functionality
| Tracker | Shirel |  | 2 | Establish each person's 2 features to implement and test
| On-Site Customer | Deji |  | 3 | Complete 2 - 4 Portfolio Assignments
| Developer | Noah
| Developer | Manon
|  | 1 | Finish Production/Admin view styling and functionality | [6 empty] | 2 | Establish each person's 2 features to implement and test
Form Styling (consistency)
Modals (pop up/error messages, etc.)
Messages (consistent and uniform throughout the app)
Pallet location button (Ask robert)
Link Hourly Reports to an order
Administration
|  | Deji |  | Initial Check CRUD
|  | Shirel |  | General View styling for an order
Update status of an order (In progress to Pending, etc.)
|  | Shirel |  | 2-step form CRUD
Set up the side menu as a "section"
|  | Shirel | Logic for multiple production lines in operation