## NL
| Name | Olagoke Ayodeji
| Year | 1 |  | NOTE: Upload this form on learn at the hand in assignment for the FRP project. You can continuesly update the form after every sprint and use it as a starting point for the next retrospective!
| PPD Level | Exploration
| Project | FRP - Den Doelder
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 1 | Start | • Pitching in more duirng meetings | • Contributing more as a group. • Attending planned meetings in person (within valid reasons). • Providing advanced notice when you can't attend. | • Highlighting reinforcements and responsibilities • Do more division of the time and work among the team members • Promote initiation • Focus on setting time aside each day to record the days work in the wiki • Planning social/group bonding activities for future sprints | • Focus on highlighting the consequences to those that remain absent/uncooperative. | 1. Discuss more the consequances about lack of communicaation, attendance and participation
| Stop | • Announcing absence minutes before class starts | • Keeping radio silence on important days | • The lack of initiation • Silence in the group meetings from some members (lack of participation) • Working beyond the set hours (unplanned sessions) | n/a | 2. Divide the time in the team so everyone has a chance to speak together with assigned responsibilities so each member can lead that section he/she is in charge of.
| Keep | • Active involvement in tasks and showing up | • Improving on team communications | • The good work progress inside the deadlines • The improvement of the communication | • Keep escalating problems and the communication | 3. Create a schedule with all the deadlines and goals for each week, sprint, wuartile both related to project and general studies. | Start
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Stop
Retro 2 | Start | • Taking up extra work after finishing the day's task(s) | • Working on completing tasks ahead of time | • Sending "heads-up" messages withing a reasonable timeframe (not last minute) • Improve on planning and allocating tasks • Completing tasks as soon as possible (don't delay until the end) | • Keeping track of their substitute during a leave/ break. | 1. Make sure to update the team on time | Keep
| Stop | • N/A (Nothing noticable for now) | • Going "radio silent" and not updating the team about issues • Diverting from the tasks allocated for a given day (thus not completing the day's work) | • Not giving a "heads up" when unable to attend team meetings/sessions in person • Postponing work until the last minute (on the schedule) | n/a | 2. During Standups make sure to discuss tasks for the next 24 hours
| Keep | • Active involvement during sprints • Interacting with team and giving feedback | • Planning on the sprintplanning tasks | • Communicating and giving updates • Focusing on priorities and adjustments • Planning work for the current/next day in the stand-ups | • Focus on highlighting the consequences to those that remain absent/uncooperative. | 3. Keep track during the workday on task progress | Start
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Stop
Retro 3 | Start |  | Doing team bonding | Having team building activites, define the tasks better, sticking to planned time slots for working |  | 1. Try and do team building activities
| Stop |  |  | Not having team building, underestimating the complexity of tasks, postponing personal assignments |  | 2. During sprint planning make sure we define and plan the tasks accordingly
| Keep | Contribution |  | Communication, Work ethics, doing the agile rituals |  | 3. Tracker needs to make sure the froup stays on schedule
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 4 | Start | infroming team of schedule | Doing team bonding | Task dividing, plan time for demos, use code reviews |  | 1. Schedule time to plan for the demo
| Stop | focusing on design too much |  | Not planning for demo prep time, not starting on final report stuff, assigning multiple people to one task |  | 2. Implement time for a code review
| Keep | comunication | Communication and Organization | Communication, Organization |  | 3. Incorporate personal assignments and report work into planning
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 5 | Start | prioritising task | Doing team bonding | Doing team bonding |  | 1. Schedule time to plan for the demo
| Stop | strenuous multitasking |  | Not doing team bonding |  | 2. Implement time for a code review
| Keep | comunication | Communication and Organization | Planning, and acting on that plan |  | 3. Incorporate personal assignments and report work into planning
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 6 | Start |  | Doing team bonding | Ask more questions and ask for clarification |  | 1. Schedule time to plan for the demo
| Stop |  |  | Stop acting before first clarifying what is needed or wanted |  | 2. Implement time for a code review
| Keep | delivering on time and communication | Communication and Organization | Commitment to the project, team-work, work ethics, comminication and updates on time |  | 3. Incorporate personal assignments and report work into planning
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 7 | Start | giving more feedback in retrospective | Doing team bonding |  |  | 1. Schedule time to plan for the demo
| Stop |  |  |  |  | 2. Do final Demo
| Keep | : delivering on time and communication and attendance | Communication and Organization | Work ethic |  | 3. Achieve a passing mark

## English
Name
| Year | 1 / 2 / 4
| PPD level | Advanced
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 1 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 2 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 3 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 4 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | My important points | Important for a team | Important according to team members | Important according to program | Action points for next quartile | Connection with PPD Quadrant
Conclusie na retro 4 | Start | My most important development this quartile was: … | What every team should pay attention to: … | My most important development this quartile was: … | What I should start with according to the program: … | 1.
| Stop | My most important stop this quartile was: …. | What no teams should do: … | My most important stop this quartile was: …. | What I should stop with according to the program: … | 2.
| Keep | My strongest point this quartile was: … | What good teams do: … | My strongest point this quartile was: … | What I should keep doing according to the program: … | 3.