## General
| Team number and/or name | Team 06 | Project name | Den Doelder (ENG)
| Date | 2022-03-06
| Vocabulary | Risk = something that can happen, which will have a negative impact on the project
Problem = a risk that has become reality; it has happened
Score = number between 1 and 25. Higher numbers point to risks that are very dangerous to your project
Risk ID | Title | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Back Up Team Member | Mitigation plan | Status
(also called Contingency plan)
# | Title here | Describe briefly but concretely what the risk contains and what the result of the risk becoming reality is. | 1 = chance of winning lottery 5 = almost guaranteed to happen | 1 = team member unavailable for a day or two 5 = team would need 4 extra sprints | Score = probablility * impact | The team member responsible for the risk | Back-up Team member | Avoid: How you will circumvent the risk in its entirety Evade: How you will lower the probability of the risk from happening Contain: How you will lower the impact of the risk if it happens | Inactive: risk is still a risk Active: Risk has become
1 | Computer malfunction (Hardware/Software) | Hardware: Computer breaks/stops working, can't use webcam/microphone for an online call, internet not working Software: Data corrupts, can't access saved files, programs not working, subscriptions failing. If any of these problems occur the risk could be either loss of information if it wasnt backed up or delys in delivery of product. | 3 | 3 | 9 | Deji |  | Avoid: Keep regular backups of code/information by committing regular updates to GitHub on a daily basis. Keep your device up to date. Don't feed your computer coffee! Evade: You avoid eating/drinking near your pc Contain: Borrow a laptop from a friend/classmate. Take part in paired programming, with other team members when working on complicated or missing features. | Inactive
2 | Can't access college facilities | You make it to the train or bus station and you are informed public transportation will not be running due to external factors or your car breaks. The risk here is causing issues with organizing team/ client meetings and attendance issues. | 3 | 2 | 6 | Nick | Valentijn | Avoid: Create backup plan to transition to remote/online meetings on short notice Evade: Keeping up to date on travel/attendance restrictions, being aware of the condition of your travel methods Contain: Implement the established remote/online working plans | Inactive
3 | Long-term ilness/absence | A team member has to quarantine / is out sick for an extended period of time / Needs to take personal time off - the risk is delys in getting the work done, that team member will be left out of the loop and miss information, it will affect the rest of the groups productivity. | 3 | 4 | 12 | Shirel | Nick | Avoid: Reduce unnecessary contacts, maintain regular communication with the team. Evade: Follow current Corona advice. Contain: In case of short-term illness, affected individuals move to remote/online working. For long-term illnesses/absences then follow the procedure in the Kick-off document. | Inactive
4 | Communication with client/staff/team | Delays in receiving client replies, not getting answers to our questions. Issues arranging meetings with the client. The risk here is missing out on critical information, misunderstanding on client needs so the final product will not match their expectations or the group will not be able to affectively plan the work. | 2 | 5 | 10 | Valentijn | Shirel | Avoid: Keep regular communication with the team/client Evade: Make sure we communicate potential issues in advance so plans can be arranged. Keep track on people. Follow Kick-off document regarding client communication issues Contain: Talk it out with the group, if it continues, escalate accordingly. | Inactive
5 | Lack of Information/Knowledge | Team members are not sure how to implement code or features into the application. We do not have enough information about specific systems/interactions about the client's systems The risk here is missing out on critical information, the group will not be able to affectively plan the work and produce a working and consistent product. | 3 | 2 | 6 | Valentijn |  | Avoid: Research the information in advance, look at the existing materials available. Evade: Communicate with the team to see if they have a solution Contain: Ask questions to the relevant subject matter experts (Lecturers/Group Members) and Client | Inactive
6 | External distractions/pressures | Work/external examination conflicts with the work or puts pressures on completing project work. Stress induced situations - the risk is delys in getting the work done, that team member will be left out of the loop and miss information, it will affect the rest of the groups productivity. | 4 | 3 | 12 | Shirel | Nick | Avoid: Plan non-project matter outside of the current project schedule Evade: Plan in advance and raise potential conflicts with the group so we can adjust accordingly Contain: Readjust the plan accordingly, schedule to complete work outside of the set hours if need. If non-essential conflicts cause further issues, discuss with team member and/or escalate to lecturer. | Inactive
0
7 | Over ambitious goals | The team sets high expectations on goals that arent achievable, reducing the quality of work on the project, causing stress and possible deadline issues. | 3 | 3 | 9 | Nick | Valentijn | Avoid: Proper sprint planning Evade: Checking each task status propearly during daily standups, keep focus on the timeline. Contain: Readjust the plan accordingly, the developers work together with the tracker to reassess the workload. | Inactive

## Sprint 3
| Team number and/or name | Team 06 | Project name | Den Doelder (ENG)
| Date | 2022-03-06
| Vocabulary | Risk = something that can happen, which will have a negative impact on the project
Problem = a risk that has become reality; it has happened
Score = number between 1 and 25. Higher numbers point to risks that are very dangerous to your project
Risk ID | Title | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Back Up Team Member | Mitigation plan | Status
(also called Contingency plan)
# | Title here | Describe briefly but concretely what the risk contains and what the result of the risk becoming reality is. | 1 = chance of winning lottery 5 = almost guaranteed to happen | 1 = team member unavailable for a day or two 5 = team would need 4 extra sprints | Score = probablility * impact | The team member responsible for the risk | Back-up Team member | Avoid: How you will circumvent the risk in its entirety Evade: How you will lower the probability of the risk from happening Contain: How you will lower the impact of the risk if it happens | Inactive: risk is still a risk Active: Risk has become
1 | Delays in the client responding | If the team require any additoinal information from the client and it is taking several days several days for us to receive a response, this could prevent us from acquiring important information relating to the tool's design or specificatoins. | 2 | 4 | 8 | Valentijn | Deji | Avoid: Establish a response timeframe for all messages/emails/calls Evade: Schedule follow up messages with the client to remind them of our request, or have a backup contact from the client that we can redirect our queries to. Contain: Raise the issue in contacting the client with the project lecturer, so they are aware and can attempt to contact them, otherwise continue working with the existing information | Inactive
2 | Project Lecturer is unavailable | Project Lecturer is unavailable for contact for a variety of reasons (personal, professional, scheduling, etc.) and the team are looking to send/receive updates or feedback to the lecturer that would impact the project or its documentation | 4 | 3 | 12 | Nick | Shirel | Avoid: Make a plan with the project lecturer to schedule any available time where we can contact them Evade: Update the contact schedule and arrange a backup project lecturer as another point of contact Contain: Direct all contact to the backup project lecturer | Inactive
3 | Team members not sufficiently contributing to the project work | Team members not focusing on the project work and "spacing out" during important meetings when they believe it is not relevant to them, thus impacting the quality of the report and coding work presented in the project | 3 | 5 | 15 | Shirel | Nick | Avoid: Keep regular updates in our Sprint stand up meetings to highlight each person's work and any issues encountered Evade: Contacting the person responsible to check up on them and see what issues they might be encountering, highlighting the risks and consequences of the issue. Contain: Escalate the issue further with the project lecturer(s) if the person responsible is not making any improvements and readjust the team's plan around the issue. | Inactive
0

## Sprint 4
| Team number and/or name | Team 06 | Project name | Den Doelder (ENG)
| Date | 2022-04-26
| Vocabulary | Risk = something that can happen, which will have a negative impact on the project
Problem = a risk that has become reality; it has happened
Score = number between 1 and 25. Higher numbers point to risks that are very dangerous to your project
Risk ID | Title | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Back Up Team Member | Mitigation plan | Status
(also called Contingency plan)
# | Title here | Describe briefly but concretely what the risk contains and what the result of the risk becoming reality is. | 1 = chance of winning lottery 5 = almost guaranteed to happen | 1 = team member unavailable for a day or two 5 = team would need 4 extra sprints | Score = probablility * impact | The team member responsible for the risk | Back-up Team member | Avoid: How you will circumvent the risk in its entirety Evade: How you will lower the probability of the risk from happening Contain: How you will lower the impact of the risk if it happens | Inactive: risk is still a risk Active: Risk has become
1 | Unavailability due to sickness of a team member | One or more team memebers may feel sick or will be unavilable because of personal reasons. The risk is a delay and that some tasks will not be completed on time increasing the workload on the rest of the team. | 3 | 3 | 9 | Shirel | Noah | Avoid: maintain regular communication with the team. Evade: reduce and control levels of stress in the group Contain: In case of short-term illness, affected individuals move to remote/online working. For long-term illnesses/absences then follow the procedure in the Kick-off document. | Active
2 | Project Lecturer is unavailable | Project Lecturer is unavailable for contact for a variety of reasons (personal, professional, scheduling, etc.) and the team are looking to send/receive updates or feedback to the lecturer that would impact the project or its documentation | 4 | 3 | 12 | Deji | Valentijn | Avoid: Make a plan with the project lecturer to schedule any available time where we can contact them Evade: Update the contact schedule and arrange a backup project lecturer as another point of contact Contain: Direct all contact to the backup project lecturer | Inactive
3 | Team members not sufficiently contributing to the project work | Team members not focusing on the project work and "spacing out" during important meetings when they believe it is not relevant to them, thus impacting the quality of the report and coding work presented in the project | 2 | 5 | 10 | Manon | Nick | Avoid: Keep regular updates in our Sprint stand up meetings to highlight each person's work and any issues encountered Evade: Contacting the person responsible to check up on them and see what issues they might be encountering, highlighting the risks and consequences of the issue. Contain: Escalate the issue further with the project lecturer(s) if the person responsible is not making any improvements and readjust the team's plan around the issue. | Inactive
4 | Computer malfunction (Hardware/Software) | Hardware: Computer breaks/stops working, can't use webcam/microphone for an online call, internet not working Software: Data corrupts, can't access saved files, programs not working, subscriptions failing. If any of these problems occur the risk could be either loss of information if it wasnt backed up or delys in delivery of product. | 3 | 3 | 9 | Nick | Manon | Avoid: Keep regular backups of code/information by committing regular updates to GitHub on a daily basis. Keep your device up to date. Don't feed your computer coffee! Evade: You avoid eating/drinking near your pc Contain: Borrow a laptop from a friend/classmate. Take part in paired programming, with other team members when working on complicated or missing features. | Active
0