## Sheet1
| Monday 30/5 | Tuesday 31/5 | Wednesday 1/6 | Thursday 2/6 | Friday 3/6 | Monday 6/6 | Tuesday 7/6 | Wednesday 8/6 | Thursday 9/6 | Friday 10/6
Overall |  | Consultancy Stuff |  |  |  | OFF | Consultancy Stuff | DEMO DAY | Consultancy Stuff
Questions for Robert
Deji |  | Personal |  |  | Administration Initial Check CRUD |  | Prodiction Batch Check CRUD Permissions | Demo Prep | Personal
Adding Pallets (Logic Fix)
Manon |  | Personal | [5 empty] | Demo Prep | Personal
[7 empty] | Notes Implemented |  |  | Business Logic (Current)
Nick |  | Personal |  |  |  |  | Changing Pallet Location Button | Demo Prep | Personal | New Business Logic
|  | Site Visit |  |  | Add Stand-up Notes Online |  | Update Hourly Check-up |  | Research Modals
Noah |  | Personal |  |  | Drawings Style Update + Add to Admin |  |  | Demo Prep | Personal
|  | Site Visit |  |  |  |  | Truck Driver
Shirel |  | Personal | Fix navigation |  |  |  |  | Demo Prep | Personal
|  |  | Picking Production Line |  | Update Order Status |  | Creating new order (2-step form)
| Team Roles |  |  | Goal:
| Team Coach | Nick |  | 1 | Finish Production/Admin view styling and functionality
| Tracker | Shirel |  | 2 | Establish each person's 2 features to implement and test
| On-Site Customer | Deji |  | 3 | Complete 2 - 4 Portfolio Assignments
| Developer | Noah
| Developer | Manon
|  | 1 | Finish Production/Admin view styling and functionality | [6 empty] | 2
Form Styling (consistency)
Modals (pop up/error messages, etc.)
Messages (consistent and uniform throughout the app)
|  |  | Pallet location button (Ask robert) |  |  |  |  | Noah | navigation style fix: minimize and active link
|  |  | Link Hourly Reports to an order |  |  |  |  | Deji | initial and prod check creation
|  |  | Administration |  |  |  |  | Nick and Manon | hourly and notes connected to an order
|  | Deji |  | Initial Check CRUD |  |  |  | Everyone | comments of functions
[8 empty] | ?? | ERD
[8 empty] | Nick | Modals
|  | Shirel |  | 2-step form CRUD |  |  |  | Everyone their own | Finish Production Styling + hourly reports styling
|  |  | Set up the side menu as a "section" |  |  |  |  | Shirel | Change navigation to "sections"
Timestamp Calculations
|  | Shirel | Logic for multiple production lines in operation |  |  |  |  | Manon and Nick | Business Process
|  |  | General View styling for an order |  |  |  |  | Everyone | Pick our features
Update status of an order (In progress to Pending, etc.)