## NL
| Name | Noah Roth
| Year | 1 |  | NOTE: Upload this form on learn at the hand in assignment for the FRP project. You can continuesly update the form after every sprint and use it as a starting point for the next retrospective!
| PPD Level | Exploration
| Project | FRP - Team 8 (Scheldtpad LLC)
|  | About myself (But from myself b/c no one else did it) | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 1 | Start | Trying to relax myself so I don't burn out on a daily basis | Attendance Sheets, Create a Daily Scenario, review the Sprint 0 plan, Implement roles |  |  | 1.
| Stop | Letting team members make excuses for poor behaviour | Procrastinating Work - we can do more with what we already know and should stop waiting and making excuses why we can't work on the project |  |  | 2.
| Keep | Trying to get this team to work | Using Google Drive for Files - Google drive is the best collaberation method for files, and also provides a constant and predictable location for files |  |  | 3.
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 2 | Start | Looking for ways to get myself into another team - this one was fine getting a 7.7 and I wasn't, and I want a team that will put effort into these things. | Stop Procrastinating, use better time management - Start being better about the use of our time and being more proactive with our scheduling | Same as Row D | Same as Row D | 1.
| Stop | Pushing the team to put in more effort - they won't budge and will turn on myself anyway, they're fairly deadline motivated | Being loose with team roles - We need to do more with the team roles as I feel they're not being used to their fullest potential | Procrastinating/Poor time management - we are often waiting until it's too late to try and finish tasks within the project | Same as Row D | 2.
| Keep | My desire to succeed | Adhearing to the more complete sprint plan - The revamped version of sprint planning has made us more succesful and reduced the overall stress on the group | Structured Planning/Keeping to the sprint plan, and good communication | Same as Row D | 3.
(New Team!) |  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Feedback from other members abt me
Retro 3 | Start | Being more proactive with my roles | being more concise with the warmups | Having team building activites, define the tasks better, sticking to planned time slots for working | n/a, no teacher present :( | 1. Try and do team building activities | Being more proactive with communication
| Stop | Stressing myself so much | having long standups? | Not having team building, underestimating the complexity of tasks, postponing personal assignments | n/a, no teacher present :( | 2. During sprint planning make sure we define and plan the tasks accordingly | Deviating from the group's schedule/not communicating changes in plans
| Keep | Putting effort into my work | assigning and using roles | Communication, Work ethics, doing the agile rituals | n/a, no teacher present :( | 3. Tracker needs to make sure the froup stays on schedule | Humor, Contributing ideas to the website, Understanding the working ways of the group
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 4 | Start | Waking up earlier, going to bed earlier | Planning more, planning for things that aren't coding | Task dividing, plan time for demos, use code reviews | n/a, no teacher present :( | 1. Schedule time to plan for the demo | Letting others do the demos, be more practive with the Tracker role
| Stop | Waking up late, procrastinating personal assignments | Panicking when things go poorly, not planning for demo prep time, not starting on final report stuff/ITP | Not planning for demo prep time, not starting on final report stuff, assigning multiple people to one task | n/a, no teacher present :( | 2. Implement time for a code review | Stop talking during demos, being an uninvolved tracker
| Keep | Being punctual | Communication and Organization | Communication, Organization | n/a, no teacher present :( | 3. Incorporate personal assignments and report work into planning | Reliability, Interactions
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 5 | Start | Getting more sleep | Doing team bonding | Doing team bonding | n/a, no teacher present :( | 1. Do something more than lunch for team bonding | Ask for help with team members
| Stop | Being incredibly spacey | Not Doing Team Bonding | Not doing team bonding | n/a, no teacher present :( | 2. Planning for Team Final Demo/Product Pitch | Being stressed about leaving in a month lol
| Keep | Planning ahead, maintaining a consistent level of work | Being flexible with having to do things | Planning, and acting on that plan | n/a, no teacher present :( | 3. Team finishes personal projects | Communication, Effort, Planning
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 6 | Start | Packing up | Turning in the project | Ask more questions and ask for clarification | n/a, no teacher present :( | 1. Pet a goose | Asking more clarifying questions
| Stop | Living in the Netherlands | Shortsighted planning, working on the project | Stop acting before first clarifying what is needed or wanted | n/a, no teacher present :( | 2. Ride a train | Time management and caution
| Keep | Biking everywhere | Communicating | Commitment to the project, team-work, work ethics, comminication and updates on time | n/a, no teacher present :( | 3. &&&&&&&&&&&&&&&&& | Communication, asking for permission to switch tasks, motivating other group members
Note on E6: I didn't realize this was supposed to be filled in, and it's too late now. ======
Note on F6: Same as row E... ======
Note on D11: OR being deadline-motivated ======

## English
Name
| Year | 1 / 2 / 4
| PPD level | Advanced
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 1 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 2 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 3 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 4 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | My important points | Important for a team | Important according to team members | Important according to program | Action points for next quartile | Connection with PPD Quadrant
Conclusie na retro 4 | Start | My most important development this quartile was: … | What every team should pay attention to: … | My most important development this quartile was: … | What I should start with according to the program: … | 1.
| Stop | My most important stop this quartile was: …. | What no teams should do: … | My most important stop this quartile was: …. | What I should stop with according to the program: … | 2.
| Keep | My strongest point this quartile was: … | What good teams do: … | My strongest point this quartile was: … | What I should keep doing according to the program: … | 3.