## NL
| Name | Nick Meade
| Year | 1 |  | NOTE: Upload this form on learn at the hand in assignment for the FRP project. You can continuesly update the form after every sprint and use it as a starting point for the next retrospective!
| PPD Level | Exploration
| Project | FRP - Den Doelder
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Connection with PPD-A Learning outcome:
Retro 1 | Start | • Letting others take the podium in meetings (let them have the chance). • Keeping things more generalised and concise. | • Contributing more as a group. • Attending planned meetings in person (within valid reasons). • Providing advanced notice when you can't attend. | • Highlighting reinforcements and responsibilities • Do more division of the time and work among the team members • Promote initiation • Focus on setting time aside each day to record the days work in the wiki • Planning social/group bonding activities for future sprints | • Focus on highlighting the consequences to those that remain absent/uncooperative. | 1. Discuss more the consequances about lack of communicaation, attendance and participation | Interacting porposfuly (feedback)
| Stop | • Being as focused on topics and timeframes. | • Keeping radio silence on important days | • The lack of initiation • Silence in the group meetings from some members (lack of participation) • Working beyond the set hours (unplanned sessions) | n/a | 2. Divide the time in the team so everyone has a chance to speak together with assigned responsibilities so each member can lead that section he/she is in charge of. | Personal Leadership
| Keep | • Friendly approach to managing the team. • The calm approach when dealing with issues. | • Improving on team communications | • The good work progress inside the deadlines • The improvement of the communication | • Keep escalating problems and the communication | 3. Create a schedule with all the deadlines and goals for each week, sprint, wuartile both related to project and general studies. | Future Oriented Oorganizing
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Connection with PPD-A Learning outcome:
Retro 2 | Start | • Be more aware of my style of talking (casually) | • Working on completing tasks ahead of time | • Sending "heads-up" messages withing a reasonable timeframe (not last minute) • Improve on planning and allocating tasks • Completing tasks as soon as possible (don't delay until the end) | n/a | 1. Make sure to update the team on time
| Stop | • N/A (Nothing noticable for now) | • Going "radio silent" and not updating the team about issues • Diverting from the tasks allocated for a given day (thus not completing the day's work) | • Not giving a "heads up" when unable to attend team meetings/sessions in person • Postponing work until the last minute (on the schedule) | n/a | 2. During Standups make sure to discuss tasks for the next 24 hours
| Keep | • The good time management • The good initiation and contributions to the team • The approach to managing the team and helping • Giving others opportunities | • Planning on the sprintplanning tasks | • Communicating and giving updates • Focusing on priorities and adjustments • Planning work for the current/next day in the stand-ups • The improvement of the communication | n/a | 3. Keep track during the workday on task progress
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Connection with PPD-A Learning outcome:
Retro 3 | Start | • Working on giving people time to explain stuff before responding. |  | • Setting time for giving/receiving feedback on work done | n/a | 1.
| Stop | • Offering immediate suggestions on solutions while people are going through an issue with their code |  | • Mixing in general conversation topics, task related topics not relevant to the stand up, set them aside for after the stand-up • Postponing work until the last moment | n/a | 2.
| Keep | • Giving others opportunities to give ideas and/or contrubite |  | • Dividing the tasks better so people don't get swamped with work | n/a | 3.
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Connection with PPD-A Learning outcome:
Retro 4 | Start | n/a |  | • Task dividing • Plan time for demos • use code reviews | Focusing more on Demo prep | 1. Structure a demo, have sessions scheduled in the sprintplanning
| Stop | n/a |  | • Not planning for demo prep time • Not starting on final report stuff • Assigning multiple people to one task when it can be easily completed by one person | n/a | 2. Implement set code review sessions.
| Keep | • Working on giving people time to explain stuff before responding. • Keeping the high level of involvement |  | • Communication • Organization | n/a | 3. Better incorporate personal assignments and report work into planning
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks | Connection with PPD Quadrant
Retro 5 | Start | n/a | n/a | n/a | n/a | 1. Prep for the final presentation
| Stop | n/a | n/a | n/a | n/a | 2. Do a non-lunch bonding
| Keep | • Keep up with the improvements on giving people time to explain stuff, improvements were noticeable. • Keeping the high level of involvement • Up the positive approach as a team coach, making people feel heard and respected, helping keep things going smoothly | • The group worked well, no issues and everything was done fast and effictively | • Keep up the work ethic going into the final week. • Working on demo prep | n/a | 3. Make sure the team passes the personal portfolio
|  | About myself | About the team (my feedback) | Team Feedback on the project | Teachers / Expert advise | Tasks
Retro 6 | Start | • Take more time scheduling personal work and avoiding last minute jobs | • Pre planning some tasks/responsibilities better, things might have been convered but not everyone was on the same line | • Asking more questions or for clarifications on tasks and info before doing/during individual work | n/a | 1.
| Stop | • Leaving tasks off until a bit later than intended | • Adding more features than necessary before other features are fully implemented | • Going ahead with tasks without seeking clarification when it might seem vague | n/a | 2.
| Keep | • Up the level of presence | • Teamwork and communication was good • People were available to help where necessary | • Team commitment to project work/teamwork • Having more feedback sessions | n/a | 3.

## English
Name
| Year | 1 / 2 / 4
| PPD level | Advanced
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 1 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 2 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 3 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | Me about myself | Me about the Team | According to team members | Feedback from Lecturer/others | Conclusion / action points | Connection with PPD-A Learning outcome:
Retro 4 | Start |  |  |  |  | 1.
| Stop |  |  |  |  | 2.
| Keep |  |  |  |  | 3.
|  | My important points | Important for a team | Important according to team members | Important according to program | Action points for next quartile | Connection with PPD Quadrant
Conclusie na retro 4 | Start | My most important development this quartile was: … | What every team should pay attention to: … | My most important development this quartile was: … | What I should start with according to the program: … | 1.
| Stop | My most important stop this quartile was: …. | What no teams should do: … | My most important stop this quartile was: …. | What I should stop with according to the program: … | 2.
| Keep | My strongest point this quartile was: … | What good teams do: … | My strongest point this quartile was: … | What I should keep doing according to the program: … | 3.